|  |
| --- |
| **MASSACHUSETTS DEPARTMENT OF ELEMENTARY AND SECONDARY EDUCATION****Program Quality Assurance Services** |

##### COORDINATED PROGRAM REVIEW

## CORRECTIVE ACTION PLAN

Charter School or District: Northboro-Southboro

CPR Onsite Year: 2017-2018

Program Area: Special Education

All corrective action must be fully implemented and all noncompliance corrected as soon as possible and no later than one year from the issuance of the Coordinated Program Review Final Report dated 08/24/2018.

**Mandatory One-Year Compliance Date:** **08/25/2019**

**Summary of Required Corrective Action Plans in this Report**

| **Criterion** | **Criterion Title** | **CPR Rating** |
| --- | --- | --- |
| SE 18B | Determination of placement; provision of IEP to parent | Partially Implemented |
| CR 17A | Use of physical restraint on any student enrolled in a publicly-funded education program | Partially Implemented |
| CR 24 | Curriculum review | Partially Implemented |
| ELE 6 | Program Exit and Readiness | Partially Implemented |
| ELE 14 | Licensure Requirements | Partially Implemented |

|  |
| --- |
| COORDINATED PROGRAM REVIEW**CORRECTIVE ACTION PLAN** |

|  |  |
| --- | --- |
| **Criterion & Topic:** SE 18B Determination of placement; provision of IEP to parent | **CPR Rating:** Partially Implemented |
| **Department CPR Findings:** A review of student records and staff interviews indicated that the district provides the parent with two (2) copies of the proposed IEP and proposed placement along with the required notice. However, these documents are not always provided to parents immediately following the development of the IEP. |
| **Description of Corrective Action:** The Department of Elementary and Secondary Education found that parents are not provided with an IEP immediately following the development of the IEP. In order to rectify this finding, the staff at the high school will be trained on timeline procedures and a record review will be conducted a few months after the training. |
| **Title/Role(s) of Responsible Persons:**Director of Student Support Services and Special Education Administrator for Instructional Support | **Expected Date of Completion:**06/15/2019 |
| **Evidence of Completion of the Corrective Action:**Evidence will be as follows:1. Training materials used to inform staff of IEP procedures2. Sign in sheets for training3. A list of 10 students records across 4 grades for review |
| **Description of Internal Monitoring Procedures:** A spreadsheet of timelines for all students' IEPs will be reviewed monthly by the Special Education Administrator.This spreadsheet will be shared with special education liaisons at department meetings for compliance review. |
| CORRECTIVE ACTION PLAN APPROVAL SECTION |
| **Criterion:** SE 18B Determination of placement; provision of IEP to parent | **Corrective Action Plan Status:** Approved **Status Date:** 10/04/2018 **Correction Status:** Not Corrected |
| **Basis for Decision:**  |
| **Department Order of Corrective Action:** |
| **Required Elements of Progress Report(s):** By January 18, 2019, submit evidence of training conducted for appropriate staff to ensure the district provides the parent with two (2) copies of the proposed IEP and proposed placement along with the required notice immediately following the development of the IEP. Evidence of training should include training materials, meeting agendas and signed attendance sheets. By March 29, 2019, submit the results of an internal review of records to ensure that the district provides the parent with two (2) copies of the proposed IEP and proposed placement along with the required notice immediately following the development of the IEP. Please include the following: 1) the number of records reviewed; 2) the number of records in compliance; 3) for any records not in compliance, determine the root cause; and 4) the specific corrective actions taken to remedy the non-compliance.\*Please note when conducting internal monitoring, the school must maintain the following documentation and make it available to the Department upon request: a) list of the student names and grade levels for the records reviewed; b) date of the review; and c) name of person(s) who conducted the review, their role(s), and signature(s). |
| **Progress Report Due Date(s):** 01/18/201903/29/2019 |

|  |
| --- |
| COORDINATED PROGRAM REVIEW**CORRECTIVE ACTION PLAN** |

|  |  |
| --- | --- |
| **Criterion & Topic:** CR 17A Use of physical restraint on any student enrolled in a publicly-funded education program | **CPR Rating:** Partially Implemented |
| **Department CPR Findings:** A review of documents and staff interviews indicated that although the school has developed written restraint prevention and behavior support policies and procedures, these do not include: methods for preventing student violence, self-injurious behavior and suicide; methods for engaging parents and youth in discussions about restraint prevention and use; and a procedure for receiving and investigating complaints. |
| **Description of Corrective Action:** The Northborough-Southborough Combined School Committee will review and revise its Physical Restraint Policy to include: methods for preventing student violence, self-injurious behavior and suicide; methods for engaging parents and youth in discussions about restraint prevention and use; and a procedure for receiving and investigating complaints. Once completed, the policy will be disseminated to teachers and posted on its policy website. |
| **Title/Role(s) of Responsible Persons:**Assistant Superintendent | **Expected Date of Completion:**06/30/2019 |
| **Evidence of Completion of the Corrective Action:**Approved Physical Restraint Policy |
| **Description of Internal Monitoring Procedures:** Review meeting schedule, meeting minutes, and school committee meetings. |
| CORRECTIVE ACTION PLAN APPROVAL SECTION |
| **Criterion:** CR 17A Use of physical restraint on any student enrolled in a publicly-funded education program | **Corrective Action Plan Status:** Approved **Status Date:** 10/04/2018 **Correction Status:** Not Corrected |
| **Basis for Decision:**  |
| **Department Order of Corrective Action:** |
| **Required Elements of Progress Report(s):** By January 18, 2019, submit updated restraint prevention and behavior support policy and procedures that incorporate all required components, including: methods for preventing student violence, self-injurious behavior and suicide; methods for engaging parents and youth in discussions about restraint prevention and use; and a procedure for receiving and investigating complaints. By March 29, 2019, provide evidence of dissemination of the revised policy to the school community inclusive of staff, students and parents. By March 29, 2019, provide evidence of training for all staff members on the revised policy. Evidence of training should include training materials, meeting agendas and signed attendance sheets. |
| **Progress Report Due Date(s):** 01/18/201903/29/2019 |

|  |
| --- |
| COORDINATED PROGRAM REVIEW**CORRECTIVE ACTION PLAN** |

|  |  |
| --- | --- |
| **Criterion & Topic:** CR 24 Curriculum review | **CPR Rating:** Partially Implemented |
| **Department CPR Findings:** A review of documents and staff interviews indicated that the district does not ensure that individual teachers review all educational materials for simplistic and demeaning generalizations, lacking intellectual merit, on the basis of race, color, sex, gender identity, religion, national origin and sexual orientation. |
| **Description of Corrective Action:** The District will develop and implement a training module focused on ensure that individual teachers review all educational materials for simplistic and demeaning generalizations, lacking intellectual merit, on the basis of race, color, sex, gender identity, religion, national origin and sexual orientation. After completing the module, teachers will be asked to review their educational materials. |
| **Title/Role(s) of Responsible Persons:**Assistant Superintendent | **Expected Date of Completion:**06/30/2019 |
| **Evidence of Completion of the Corrective Action:**Creation of training moduleTraining completion log and review of educational materials |
| **Description of Internal Monitoring Procedures:** Completion logs of learning module will be reviewedThe training module will be review annually |
| CORRECTIVE ACTION PLAN APPROVAL SECTION |
| **Criterion:** CR 24 Curriculum review | **Corrective Action Plan Status:** Approved **Status Date:** 10/04/2018 **Correction Status:** Not Corrected |
| **Basis for Decision:**  |
| **Department Order of Corrective Action:** |
| **Required Elements of Progress Report(s):** By January 18, 2019, provide a copy of the procedures developed to ensure that individual teachers in the district review educational materials for consideration of simplistic and demeaning generalizations, lacking intellectual merit, on the basis of race, color, sex, gender identity, religion, national origin and sexual orientation.By March 29, 2019, submit evidence of training provided to all teachers to ensure they review all educational materials for consideration of simplistic and demeaning generalizations, lacking intellectual merit, on the basis of race, color, sex, gender identity, religion, national origin and sexual orientation. Evidence of training should include training materials, meeting agendas and signed attendance sheets. |
| **Progress Report Due Date(s):** 01/18/201903/29/2019 |

|  |
| --- |
| COORDINATED PROGRAM REVIEW**CORRECTIVE ACTION PLAN** |

|  |  |
| --- | --- |
| **Criterion & Topic:** ELE 6 Program Exit and Readiness | **CPR Rating:** Partially Implemented |
| **Department CPR Findings:** A review of the documentation indicated that the district reclassified a student as a Former English Learner (FEL) before the student met the minimum exit criteria determined by the Department. The district's current reclassification practices are not in compliance with 603 CMR 14.02 that requires districts to establish exit criteria in accordance with the Department guidelines. |
| **Description of Corrective Action:** The district reclassified a student before the student met the minimum exit criteria determined by the Department. In order to rectify this, the district will revise the English Language Reclassification document to state that no English Learner can be reclassified if a student has not met the minimum reclassification criteria. The newly revised document will be shared at an ELD staff meeting. |
| **Title/Role(s) of Responsible Persons:**Director of English Language Education | **Expected Date of Completion:**12/12/2018 |
| **Evidence of Completion of the Corrective Action:**The evidence of completion will be the following:1. The revision of the Northborough-Southborough English Language Reclassification document. 2. The agenda of an ELD staff meeting that includes the revised Northborough-Southborough English Language Reclassification document.3. The list of reclassified English Learners in September 2018 uploaded to the Department. |
| **Description of Internal Monitoring Procedures:** The Director of English Language Education will oversee the reclassification decisions made for all English Learners to ensure that no English Learner is reclassified if a student has not met the minimum reclassification criteria. The English Language Reclassification document will be reviewed with the ELD staff every year. |
| CORRECTIVE ACTION PLAN APPROVAL SECTION |
| **Criterion:** ELE 6 Program Exit and Readiness | **Corrective Action Plan Status:** Approved **Status Date:** 10/04/2018 **Correction Status:** Not Corrected |
| **Basis for Decision:**  |
| **Department Order of Corrective Action:** |
| **Required Elements of Progress Report(s):** 1-By March 29, 2019, submit the district's revised reclassification policies and procedures. 2- Provide training to all staff members involved in the reclassification process to ensure that they are all knowledgeable about the changes and submit the training materials, sign-in sheets and agendas. 3-By July 5, 2019, complete the FEL Roster available in the Document Library to provide information for all the ELs in your district who have been reclassified in the SY 2018-19. |
| **Progress Report Due Date(s):** 03/29/201907/05/2019 |

|  |
| --- |
| COORDINATED PROGRAM REVIEW**CORRECTIVE ACTION PLAN** |

|  |  |
| --- | --- |
| **Criterion & Topic:** ELE 14 Licensure Requirements | **CPR Rating:** Partially Implemented |
| **Department CPR Findings:** Staff interviews and the relevant SEI endorsement data indicated that most core academic teachers assigned to provide sheltered English instruction to English learners hold the SEI Teacher Endorsement, but some do not. |
| **Description of Corrective Action:** The District has placed most English Learners (ELs), but not all ELs, with core academic teachers who hold the SEI Endorsement. In order to ensure that all ELs are placed with SEI Endorsed Teachers, the district with take the following steps:1. Identify and notify non-endorsed core academic teachers of their professional obligation to receive the SEI endorsement within the school calendar year if an EL is placed in their classroom.2. Communicate to Administrators the Department's regulations regarding placement of ELs.3. Provide opportunities for core-academic teachers to meet their obligations to get the SEI endorsement.4. At the conclusion of each year, follow up with each non-endorsed core academic teacher to ensure they have followed up with their obligation of becoming SEI endorsed. |
| **Title/Role(s) of Responsible Persons:**Principals, ELE Director, and Assistant Superintendent | **Expected Date of Completion:**06/30/2019 |
| **Evidence of Completion of the Corrective Action:**1. List of non-endorsed core academic teachers. 2. Notify non-endorsed core academic teachers of their professional obligation to receive the SEI endorsement within the school calendar year if an EL is placed in their classroom.3. Review list of non-endorsed core academic teachers to confirm that they have obtained the SEI endorsement.4. Copy of communications to Administrators regarding Department's regulations of placement of ELs. |
| **Description of Internal Monitoring Procedures:** Every year the placement of ELs will be reviewed to ensure that ELs are placed with SEI endorsed core academic teachers. |
| CORRECTIVE ACTION PLAN APPROVAL SECTION |
| **Criterion:** ELE 14 Licensure Requirements | **Corrective Action Plan Status:** Approved **Status Date:** 10/04/2018 **Correction Status:** Not Corrected |
| **Basis for Decision:**  |
| **Department Order of Corrective Action:** |
| **Required Elements of Progress Report(s):** 1- Provide information on the support the district will provide to help the unendorsed educator(s) earn their endorsement and a timeline that shows the educators' efforts towards earning their SEI endorsement.2- Please submit the district's plan to ensure that ELs are assigned only to core academic teachers who hold the SEI endorsement.3- Please provide training to district administrators to ensure compliance with procedure and placement of students. Submit the training materials, sign-in sheets and agendas by the progress report due date.4- Please submit the completed SEI endorsement form available in the Document Library to provide information regarding the SEI endorsement status of the core academic teachers of ELs in the district. |
| **Progress Report Due Date(s):** 01/18/2019 |