| Requirement | Action | Proposed Date |
| --- | --- | --- |
| Regulations |  |  |
| Promulgate regulations on School and District Accountability/Assistance | Presented draft regulations on Level 4 school identification for discussion and vote to solicit public comment | January 26, 2010 |
| Promulgate regulations on School and District Accountability/Assistance | Present revised regulation on Level 4 school identification for approval | March 23, 2010 |
| Promulgate regulations on School and District Accountability/Assistance | Presented draft regulations on School and District Accountability and Assistance to the Board for discussion and vote to solicit public comment | February 23, 2010 |
| Promulgate regulations on Charter Schools | Present proposed amendments to Charter School regulations to the Board for discussion and vote to solicit public comment | March 23, 2010 |
| Promulgate regulations on Innovation Schools, including virtual schools | Present proposed regulations on Innovation Schools, including virtual schools, to the Board for discussion and vote to solicit public comment | April 27, 2010 |
| Promulgate regulations on School and District Accountability/Assistance | Vote to adopt final regulations | April 27, 2010 |
| Promulgate regulations on Charter Schools | Vote to adopt final regulations | May 25, 2010 |
| Promulgate regulations on Innovation Schools | Vote to adopt final regulations | June 22, 2010 |
| Implementation: School and District Accountability and Assistance |  |  |
| Lowest 20 percent of schools | Develop a single measure to identify schools that score in the lowest 20 percent statewide among schools serving common grade levels, that takes into account student performance data | Completed March 2010 |
| Student academic improvement factor | Develop a plan to implement the inclusion of improvement in student academic achievement data | January 1, 2011 |
| Student academic improvement factor | Implement the inclusion of improvement in student academic achievement data | September 2011 |
| Receiver evaluation | Develop guidelines for the written evaluation of a receiver | June 2011 |
| Level 4 school | Designate Level 4 schools | March 4, 2010 Identified 35 “likely” |
| Turnaround Plans | Develop guidelines for a Level 4 turnaround plan | March 2010 |
| Coordination with other state agencies | Develop guidelines to assist in facilitating turnaround plans and coordination of other state and local services | June 2010 |
| Annual Review | Determine a format for the annual review of Level 4 schools and the appointment of an external examiner (if needed) for July 1, 2011 implementation by superintendents | January 2011 |
| Commissioner’s Evaluation of the Annual Progress Review | Determine evaluation criteria of the annual performance goals and subsequent action | October 2010 |
| Three Year Review | Determine procedures to conduct a review of the school and criteria to determine whether the school has improved sufficiently, requires further improvement or has failed to improve | October 2012 |
| Level 5 Schools | Develop guidelines for a turnaround plan for a Level 5 school | October 2012 |
| Quarterly Report and Annual Evaluation | Develop a template for quarterly reporting and an annual evaluation of a Level 5 school to the superintendent and school committee | October 2012 |
| Lowest 10 percent of districts | Develop a single measure that takes into account student achievement data to determine lowest 10 percent of districts | June 2010 |
| Level 5 Districts | Establish guidelines for creating a district turnaround plan | October 2010 |
| Annual Review | Determine a format for the annual review of Level 5 district performance | October 2010 |
| Municipal Fiscal Failure | Establish guidelines for declaring a school district as Level 5 if a municipality has failed to fulfill its fiscal responsibilities | October 2010 |
| Implementation: Charter Schools |  |  |
| List of districts eligible under cap lift | Determine districts in the lowest 10 percent of all statewide student performance scores | April 2010 Draft |
| Charter School Application | Revise charter school application | April 2010 |
| Application Approval Criteria | Update criteria for the approval of a charter application | April 2010 |
| Renewal of a Charter | Revise charter renewal checklist | May 2010 |
| Recruitment and Retention Plan | Establish guidelines for recruitment and retention plan | May 2010 |
| Recruitment and Retention Plan | Notify charter schools of requirement to have a recruitment and retention plan in effect for the 2011-2012 school year | May 2010 |
| Third Party Mail House | Authorize a third party mail house for use by the districts and charter school applicants | June 2010 |
| Waitlist | Establish guidelines and waitlist procedures for filling a vacancy | June 1, 2010 for annual reporting |
| Charter School Net Asset Balance | Set requirements for reporting a charter school’s net asset balance at the end of the fiscal year | June 2010 |
| Charter School Annual Audit | Review charter school annual audit guidelines | June 2010 |
| Horace Mann Technical Assistance | Provide technical assistance to school districts interested in developing a Horace Mann Charter School application | April 2010 |
| Dissemination of successful innovation | Disseminate successful innovation programs and provide technical assistance for district replication | Ongoing |
| Model Policy for Re-entry to School District | Draft policy for school districts regarding the grade placement and eligibility for high school graduation of students leaving a Commonwealth charter school and seeking to enroll in a district school | June 2010 |
| Charter School Public Hearings | Board member attends public hearing in the school district of the proposed charter school | December 2010 (done in 2009) |
| Award Commonwealth and Horace Mann charters | Make recommendations to the Board on new charter school applicants based on the revised charter school law | February 2011 |
| Collective Purchasing | Notify charter schools regarding collective purchasing provision | February 2010 |
| Education Collaboratives | Notify charter schools regarding eligibility to join an educational collaborative | February 2010 |
| Charter School Reimbursement | Calculate appropriate payments under the new payment schedule | 2012 |
| Implementation: Innovation Schools |  |  |
| Innovation Plan | Establish guidelines for other measures of achievement that may be used in an innovation plan | June 2010 |
| Annual Evaluation | Establish guidelines for the annual evaluations to be submitted to the commissioner annually | June 2010 |
| Planning and Implementation Grants | Prepare RFPs and administer grant program | Pending funding |
| Technical Assistance | Provide technical assistance and support to eligible applicants | Pending funding |
| Best practices | Collect and disseminate best practices that may be adopted by other schools | June 2011 |
| Reports | Subject Matter | Proposed Date |
| Charter School Study | On the possibility of allowing students living outside of the Commonwealth who are eligible to attend a public school to be eligible to attend charter schools-to the Joint Committee on Education | August 15, 2010 |
| Charter School Cumulative Surplus Revenue Report | On certification of the amounts in excess of 20 percent of the school’s operating budget and its capital cost for the fiscal year-to the school committee of the sending district(s) and applicable board of selectmen or city council | December 1, 2010; annually |
| Charter School Student Data Collection | On student data: racial, ethnic and socio-economic status and the number of students enrolled with IEPs and those requiring English language learners programs-to the Legislature | December 1, 2010; annually |
| Inclusion of Growth in Intervention | On the Department’s plan to implement the inclusion of improvement in student academic achievement data-to the Joint Committee on Education | January 1, 2011 |
| School and District Intervention | On the implementation and fiscal impact of underperforming and chronically underperforming schools and chronically underperforming districts-to the Legislature | August 1, 2011; annually |
| School Finance Study | On the status of the public education financing system in the Commonwealth as it currently exists-to the Joint Committee on Education | December 31, 2011 |
| Innovation Schools | On the implementation and fiscal impact of Innovation Schools-to the Legislature | December 31, 2011; annually |