**Review of 2003 Massachusetts History and Social Science Curriculum Framework**

***Plan and Timeline***

**Phase 1** (July 2016-June 2017):

Gather recommendations for the vision and structure of the framework through online survey; convene framework review panel

**Phase 2** (July-December 2017):

Draft and review proposed revisions

**Phase 3** (January-June 2018):

Present draft of proposed revisions to the Board for discussion and a vote to invite public comment; conduct public comment period, synthesize comments, make final revisions and present to the Board for discussion and a vote on whether to adopt them

**Phase 4** (July 2018-June 2020):

Disseminate updated framework to schools and support implementation

**Phase 5** (TBD):

Develop state History and Social Science assessment and administer first assessment

**Phase 6** (TBD):

Incorporate History and Social Science assessment into the Competency Determination required for high school graduation