5-Step Plan for World Languages Framework Revision

* Phase I (August-September 2019)
	+ DESE Advisory Committee Formation (already formed)
	+ Applications for Facilitator/Reviewer Teams (1.5 months)
* Phase II (October-November 2019)
	+ RFR for Vendor (1 month)
	+ Facilitator Team Selection (2 weeks)
	+ Review Panel Selection (2 weeks)
	+ Front-matter (2 months)
* Phase III (December – June 2020)
	+ Selection of Vendor (2 months, including bidding window)
	+ Draft of Revised Standards w/embedded SEL (7 months)
	+ Vendor-led Focus-group feedback of content advisors (1 month)
* Phase IV (July-November 2020)
	+ Focus Group Feedback of content advisors (1 month)
	+ Production of Public Comment Survey (2 weeks)
	+ Draft for BESE Approval for Public Comment (2 months)
* Phase V (December-March 2021)
	+ Presentation for Board of Education (2 weeks)
	+ Vendor QRGs (2 months)
	+ Final Draft of Standards based off Public Feedback (2 months, including 6 week Public Comments Window)
	+ Final Presentation to the Board (2 weeks)
	+ Implementation Plan (1 month)