## Blank Template
"Sample School District" Activity Timeline SY20-21
District/ School | Month | Date | Time/ Hours | Activity | Topic | Materials | Location | Facilitator | Participants | Goal | Additional Notes

## Leadership
"Sample School District" Activity Timeline SY20-21
District/ School | Month | Date | Time/ Hours | Activity | Topic | Materials | Location | Facilitator | Participants | Goal | Additional Notes
District | 01_August |  |  | LLTM | Review membership of District Literacy Leadership Team. Create plan & recruit teachers from under-represented grade-levels/content areas | District Literacy Plan, Activity Timeline, Communication Plan, Meeting Agenda |  |  | DLLT | 1
District | 02_September |  |  | LLTM | Finalize/Review Plans | District Literacy Plan, Activity Timeline, Communication Plan, Meeting Agenda |  |  | DLLT | 1
District | 03_October |  |  | LLTM | Review District Wide Data | District Literacy Plan, Activity Timeline, Communication Plan, Meeting Agenda |  |  | DLLT | 1
District | 04_November |  |  | LLTM | Review current DLP Review Implementation Data | District Literacy Plan, Activity Timeline, Communication Plan, Meeting Agenda |  |  | DLLT | 1
District | 05_December |  |  | LLTM |  | District Literacy Plan, Activity Timeline, Communication Plan, Meeting Agenda |  |  | DLLT | 1
District | 06_January |  |  | LLTM | Review current DLP | District Literacy Plan, Activity Timeline, Communication Plan, Meeting Agenda |  |  | DLLT | 1
District | 07_February |  |  | LLTM | Review District Wide Data | District Literacy Plan, Activity Timeline, Communication Plan, Meeting Agenda |  |  | DLLT | 1
District | 08_March |  |  | LLTM | Review Implementation Data Begin DLP for SY21/22 | District Literacy Plan, Activity Timeline, Communication Plan, Meeting Agenda |  |  | DLLT | 1
District | 09_April |  |  | LLTM | Review current DLP Draft DLP for SY21/22 | District Literacy Plan, Activity Timeline, Communication Plan, Meeting Agenda |  |  | DLLT | 1
District | 10_May |  |  | LLTM | Finalize/Review Plans for SY21/22 | District Literacy Plan, Activity Timeline, Communication Plan, Meeting Agenda |  |  | DLLT | 1
District | 11_June |  |  | LLTM | Review current DLP Review District Wide Data | District Literacy Plan, Activity Timeline, Communication Plan, Meeting Agenda |  |  | DLLT | 1
District |  |  |  | LLTM | Build Curriculum Framework | Curriculum Framework Template, Program Survey Results |  |  | DLLT | 1
District |  |  |  | LLTM | Build Assessment Framework | Assessment Framework Template, Assessment Survey Results |  |  | DLLT | 1
Elementary Schools |  |  |  | Walkthroughs | Implementation Walkthroughs | Walkthough Tool |  |  | Elementary Principals | 1
School A | 02_September |  |  | LLTM | Share communications from DLLT Mtg and get feedback to bring back to DLLT Mtg | Meeting Agenda |  | Principal | School-based LLT | 1
School A | 03_October |  |  | LLTM | Share communications from DLLT Mtg and get feedback to bring back to DLLT Mtg Review School-Wide Data | Meeting Agenda |  | Principal | School-based LLT | 1
School A | 04_November |  |  | LLTM | Share communications from DLLT Mtg and get feedback to bring back to DLLT Mtg | Meeting Agenda |  | Principal | School-based LLT | 1
School A | 05_December |  |  | LLTM | School-based LLT to share communications from DLLT Mtg and get feedback to bring back to DLLT Mtg Review Implementation Data | Meeting Agenda |  | Principal | School-based LLT | 1
School A | 06_January |  |  | LLTM | Share communications from DLLT Mtg and get feedback to bring back to DLLT Mtg | Meeting Agenda |  | Principal | School-based LLT | 1
School A | 07_February |  |  | LLTM | Share communications from DLLT Mtg and get feedback to bring back to DLLT Mtg Review School-Wide Data | Meeting Agenda |  | Principal | School-based LLT | 1
School A | 08_March |  |  | LLTM | Share communications from DLLT Mtg and get feedback to bring back to DLLT Mtg Review Implementation Data | Meeting Agenda |  | Principal | School-based LLT | 1
School A | 09_April |  |  | LLTM | Share communications from DLLT Mtg and get feedback to bring back to DLLT Mtg | Meeting Agenda |  | Principal | School-based LLT | 1
School A | 10_May |  |  | LLTM | Share communications from DLLT Mtg and get feedback to bring back to DLLT Mtg Review Implementation Data | Meeting Agenda |  | Principal | School-based LLT | 1
School A | 11_June |  |  | LLTM | Share communications from DLLT Mtg and get feedback to bring back to DLLT Mtg Review School-Wide Data | Meeting Agenda |  | Principal | School-based LLT | 1

## Tiered Instruction
"Sample School District" Activity Timeline SY20-21
District/ School | Month | Date | Time/ Hours | Activity | Topic | Materials | Location | Facilitator | Participants | Goal | Additional Notes
Elementary Schools |  |  |  | PD | Master Schedule PD | Training Materials |  |  | Elementary Principals | 2
Elementary Schools |  |  |  | Walkthroughs | Master Schedule Implementation | Master Schedule |  | Other | Admin Team | 2
Elementary Schools |  |  |  | PD | Small Group Differentiation PD | Training Materials |  | External Facilitator | K-5 Teachers | 2
District |  |  |  | LLTM | Build Curriculum Framework | Curriculum Framework Template, Program Survey Results |  |  | DLLT | 2
District |  |  |  | LLTM | Core Program Evaluation | Evaulation Tools, Sample Materials |  |  | K-5 Teachers | 2
District |  |  |  | PD | Initial Training of new program | Training Materials |  | External Facilitator | K-5 Teachers | 2
District |  |  |  | PD | Additional training of new program | Training Materials |  | External Facilitator | K-5 Teachers | 2
District |  |  |  | PD | Training in program technology | Training Materials, Site login information |  | External Facilitator | K-5 Teachers | 2
District |  |  |  | PD | Training for current programs for new staff | Training Materials |  | External Facilitator | K-5 Teachers | 2
District |  |  |  | Department Mtg | Develop Pacing Guide | Curriculum framework, program materials |  | ELA Coordinator | ELA Department | 2
Elementary Schools |  |  |  | Grade-Level Mtg | Develop Whole Group/Small Group Plan by Grade-level | Whole Group/Small Group Template |  | Reading Teacher | K-5 Teachers | 2
Elementary Schools |  |  |  | Grade-Level Mtg | Develop Small Group Plans | Small Group Plan Template, Whole Group/Small Group Template |  | Reading Teacher | K-5 Teachers | 2
District |  |  |  | Department Mtg | Develop process for collecting implementation data | Program resources, existing walkthrough tools |  | ELA Coordinator | ELA Department | 2
District |  |  |  | Department Mtg | Develop procudure for documenting the intensification of instruction for Tier 2 & 3 students |  |  | ELA Coordinator | ELA Department | 2
District |  |  |  | Walkthroughs | Collect Implementation Data | Walkthrough Tool |  | ELA Coordinator | Admin Team | 2
District |  |  |  | Department Mtg | Review assessment and implementation data for Tier 2 & 3 students | Assessment data management systems (or reports), implementation data |  | ELA Coordinator | ELA Department | 2
District |  |  |  | Department Mtg | Develop communication plan for notifying families of intervention plans or PLPs. |  |  | ELA Coordinator | ELA Department | 2020-02-05

## Professional Development
"Sample School District" Activity Timeline SY20-21
District/ School | Month | Date | Time/ Hours | Activity | Topic | Materials | Location | Facilitator | Participants | Goal | Additional Notes
District |  |  |  | PD | Professional Develop based on current reading research | Training Materials |  | External Facilitator | K-5 Teachers | 3
School A |  |  |  | Staff Mtg | Workshop on the Reading Brain | Training Materials |  | External Facilitator | K-5 Teachers | 3
School A |  |  |  | Grade-Level Mtg | Embedded PD on Phonemic Awareness | Training Materials |  | External Facilitator | K-2 Teachers | 3
District |  |  |  | Department Mtg | Create protocols for coaching cycles, model lessons, co-taught lessons, observation, and feedback | All program guiding documents (Pacing Guide, Whole/Small Group Plans, Small Group Plans) |  | ELA Coordinator | ELA Department | 3
District |  |  |  | PD
District |  |  |  | PD
District |  |  |  | PD
District |  |  |  | PD

## Assessment
"Sample School District" Activity Timeline SY20-21
District/ School | Month | Date | Time/ Hours | Activity | Topic | Materials | Location | Facilitator | Participants | Goal | Additional Notes
District |  |  |  | LLTM | Develop Assessment Framework | Assessment Framework Template, Assessment Survey Results |  |  | DLLT | 4
K-5 Teachers |  |  |  | PD | Training for new assessment | Training Materials |  |  |  | 4
District |  |  |  | Department Mtg | Develop Data Meeting Protocol | Assement Framework |  | ELA Coordinator | ELA Department | 4
District | 01_August |  |  | Testing | Migrate Students in Assessment Systems & enable progress monitoring if all are being enabled | Assessment Systems |  | District Tech |  | 4
District | 02_September |  |  | Testing | Refresher Training and Calibration | List assessments |  |  |  | 4
District | 02_September |  |  | Testing | Disseminate Testing Memo | Testing Memo Template |  |  |  | 4
District | 02_September |  |  | Testing | Testing Window | List assessments |  |  |  | 4
District | 02_September |  |  | Testing | Data entry due date |  |  |  |  | 4
District | 02_September |  |  | Testing | Confirm data entry is complete & export student data | Data Management System |  | District Tech |  | 4
District | 03_October | 3 days prior to meeting |  | Testing | Import student data into data management system | Data Management System |  | District Tech |  | 4
District | 03_October | 1 week prior to meeting |  | Testing | Prepare for Data Meetings | Meeting Agenda Template, Reports |  |  |  | 4
District | 03_October | 1 week prior to meeting |  | Data Meeting | Disseminate Data Meeting Memo | Data Meeting Memo Template |  |  |  | 4
School A | 03_October |  |  | Data Meeting | Fall Benchmark Data Meetings | Data Management System, Reports |  |  |  | 4
School B | 03_October |  |  | Data Meeting | Fall Benchmark Data Meetings | Data Management System, Reports |  |  |  | 4
District | 03_October | Within 1 week of Data Mtg |  | Testing | Communicate Progress Monitoring Plan & distribute materials | Progress Monitoring Materials, PM Calendar |  |  |  | 4
District | 05_December | 1 week prior to meeting |  | Testing | Prepare for Data Meetings | Meeting Agenda Template, Reports |  |  |  | 4
District | 05_December | 1 week prior to meeting |  | Data Meeting | Disseminate Data Meeting Memo | Data Meeting Memo Template |  |  |  | 4
School A | 05_December |  |  | Data Meeting | December Progress Monitoring Data Meetings | Data Management System, Reports |  |  |  | 4
School B | 05_December |  |  | Data Meeting | December Progress Monitoring Data Meetings | Data Management System, Reports |  |  |  | 4
District | 05_December | Within 1 week of Data Mtg |  | Testing | Communicate Progress Monitoring Plan & distribute materials | Progress Monitoring Materials, PM Calendar |  |  |  | 4
District | 06_January |  |  | Testing | Refresher Training and Calibration | List assessments |  |  |  | 4
District | 06_January |  |  | Testing | Disseminate Testing Memo | Testing Memo Template |  |  |  | 4
District | 06_January |  |  | Testing | Testing Window | List assessments |  |  |  | 4
District | 06_January |  |  | Testing | Data entry due date |  |  |  |  | 4
District | 06_January |  |  | Testing | Confirm data entry is complete & export student data | Data Management System |  | District Tech |  | 4
District | 07_February | 3 days prior to meeting |  | Testing | Import student data into data management system | Data Management System |  | District Tech |  | 4
District | 07_February | 1 week prior to meeting |  | Testing | Prepare for Data Meetings | Meeting Agenda Template, Reports |  |  |  | 4
District | 07_February | 1 week prior to meeting |  | Data Meeting | Disseminate Data Meeting Memo | Data Meeting Memo Template |  |  |  | 4
School A | 07_February |  |  | Data Meeting | Winter Benchmark Data Meetings | Data Management System, Reports |  |  |  | 4
School B | 07_February |  |  | Data Meeting | Winter Benchmark Data Meetings | Data Management System, Reports |  |  |  | 4
District | 07_February | Within 1 week of Data Mtg |  | Testing | Communicate Progress Monitoring Plan & distribute materials | Progress Monitoring Materials, PM Calendar |  |  |  | 4
District | 09_April | 1 week prior to meeting |  | Testing | Prepare for Data Meetings | Meeting Agenda Template, Reports |  |  |  | 4
District | 09_April | 1 week prior to meeting |  | Data Meeting | Disseminate Data Meeting Memo | Data Meeting Memo Template |  |  |  | 4
School A | 09_April |  |  | Data Meeting | April Progress Monitoring Data Meetings | Data Management System, Reports |  |  |  | 4
School B | 09_April |  |  | Data Meeting | April Progress Monitoring Data Meetings | Data Management System, Reports |  |  |  | 4
District | 09_April | Within 1 week of Data Mtg |  | Testing | Communicate Progress Monitoring Plan & distribute materials | Progress Monitoring Materials, PM Calendar |  |  |  | 4
District | 10_May |  |  | Testing | Refresher Training and Calibration | List assessments |  |  |  | 4
District | 10_May |  |  | Testing | Disseminate Testing Memo | Testing Memo Template |  |  |  | 4
District | 10_May |  |  | Testing | Testing Window | List assessments |  |  |  | 4
District | 10_May |  |  | Testing | Data entry due date |  |  |  |  | 4
District | 10_May |  |  | Testing | Confirm data entry is complete & export student data | Data Management System |  | District Tech |  | 4
District | 11_June | 3 days prior to meeting |  | Testing | Import student data into data management system | Data Management System |  | District Tech |  | 4
District | 11_June | 1 week prior to meeting |  | Testing | Prepare for Data Meetings | Meeting Agenda Template, Reports |  |  |  | 4
District | 11_June | 1 week prior to meeting |  | Data Meeting | Disseminate Data Meeting Memo | Data Meeting Memo Template |  |  |  | 4
School A | 11_June |  |  | Data Meeting | Spring Benchmark Data Meetings | Data Management System, Reports |  |  |  | 4
School B | 11_June |  |  | Data Meeting | Spring Benchmark Data Meetings | Data Management System, Reports |  |  |  | 4

## Home-School
"Sample School District" Activity Timeline SY20-21
District/ School | Month | Date | Time/ Hours | Activity | Topic | Materials | Location | Facilitator | Participants | Goal | Additional Notes
District | 02_September |  |  | Community Event | Back to School Night: Share about new curriculum | Family Letter from new program |  | Principal |  | 5
District |  |  |  | Community Event | Literacy Night: Share about program and Tiered Instructional Model | Program resources; home-school connection activities |  | Reading Teacher |  | 5
District |  |  |  | Community Event | Read Across America |  |  | Reading Teacher |  | 5
District |  |  |  | Department Mtg | Develop communication plan for notifying families of intervention plans or PLPs. |  |  | ELA Coordinator | ELA Department | 2020-02-05
Elementary Schools |  |  |  | Community Event | Parent Teacher Conferences |  |  | Other |  | 5
District |  |  |  | LLTM | Subcommittee meeting for creating protocols for student behavior management that are culturally-responsive |  |  |  |  | 1, 5

## LISTS_Edit Me
Edit these dropdown list to meet the needs of your district.
DistrictSchool | Month | Activity | Facilitator | Participants | Goal
District | 01_August | District Admin Mtg | ELA Coordinator | DLLT | 1
Elementary Schools | 02_September | Department Mtg | Principal | School-based LLT | 2
Middle Schools | 03_October | Staff Mtg | Reading Teacher | ELA Department | 3
K-5 Teachers | 04_November | Grade-Level Mtg | External Facilitator | Reading Teachers | 4
School A | 05_December | LLTM | District Tech | K-5 Teachers | 5
School B | 06_January | PD | Other | K-2 Teachers | 1, 2
| 07_February | Data Meeting |  | 3-5 Teachers | 1, 3
| 08_March | Testing |  | 5-6 Teachers | 1, 4
| 09_April | Walkthroughs |  | 7-8 Teachers | 1, 5
| 10_May | Community Event |  | High School ELA Teachers | 1 - 4
| 11_June |  |  | Elementary Principals | 1 - 5
|  |  |  | Middle School Principals | 2, 5
High School Principals
All Principals
Admin Team

## SAMPLE
"Sample School District" Activity Timeline SY20-21
District/ School | Month | Date | Time/ Hours | Activity | Topic | Materials | Location | Facilitator | Participants | Goal | Additional Notes
District | 01_August | 2020-08-21 |  | Testing | Migrate Students in Assessment Systems & enable progress monitoring if all are being enabled | Assessment Systems |  | District Tech |  | 4
District | 01_August | 2020-08-24 | Half Day A.M. | PD | Training for current programs for new staff | Training Materials | High School | External Facilitator | K-5 Teachers | 3
Elementary Schools | 01_August | 2020-08-25 | Full Day | PD | Initial Training in new Program | Training Materials, program materials | High School | External Facilitator | K-5 Teachers | 2
District | 01_August | 2020-08-27 | 1:00-2:30 | LLTM | Review membership of District Literacy Leadership Team. Create plan & recruit teachers from under-represented grade-levels/content areas | District Literacy Plan, Activity Timeline, Communication Plan, Meeting Agenda |  | ELA Coordinator | DLLT | 1
District | 02_September | 2020-09-03 | 3:15-4:45 | LLTM | Finalize/Review Plans | District Literacy Plan, Activity Timeline, Communication Plan, Meeting Agenda | Middle School Library | ELA Coordinator | DLLT | 1
School A | 02_September | 2020-09-08 | 3:15-4:15 | LLTM | Share communications from DLLT Mtg and get feedback to bring back to DLLT Mtg | Meeting Agenda | School Library | Principal | School-based LLT | 1
District | 02_September | 2020-09-08 | 1:00-3:00 | Department Mtg | Develop Pacing Guide | Curriculum framework, program materials | Admin Office Conference Room | ELA Coordinator | ELA Department | 2
School B | 02_September | 2020-09-09 | 3:15-4:15 | LLTM | Share communications from DLLT Mtg and get feedback to bring back to DLLT Mtg | Meeting Agenda | School Cafeteria | Principal | School-based LLT | 1
District | 02_September | 2020-09-14 |  | Testing | Disseminate Testing Memo | Testing Memo Template |  | Reading Teacher | K-5 Teachers | 4
District | 02_September | 9/14/20-9/23/20 |  | Testing | Refresher Training and Calibration | List assessments |  | Reading Teacher | K-5 Teachers | 4
District | 02_September | 9/21/20-10/9/20 |  | Testing | Testing Window | List assessments |  |  |  | 4
District | 03_October | 2020-10-03 | 3:15-4:45 | LLTM | Build Curriculum Framework | Curriculum Framework Template, Program Survey Results | Middle School Library | ELA Coordinator | DLLT | 2
School A | 03_October | 2020-10-08 | 3:15-4:15 | LLTM | Share communications from DLLT Mtg and get feedback to bring back to DLLT Mtg | Meeting Agenda | School Library | Principal | School-based LLT | 1
District | 03_October | 2020-10-09 |  | Testing | Data entry due date |  |  |  |  | 4
School B | 03_October | 2020-10-09 | 3:15-4:15 | LLTM | Share communications from DLLT Mtg and get feedback to bring back to DLLT Mtg | Meeting Agenda | School Cafeteria | Principal | School-based LLT | 1
District | 03_October | 2020-10-12 |  | Testing | Confirm data entry is complete & export student data | Data Management System |  | District Tech |  | 4
School A | 03_October | 2020-10-12 | 3:15-4:15 | Staff Mtg | Workshop on the Reading Brain | Training Materials | School Library | External Facilitator | K-5 Teachers | 3
District | 03_October | 2020-10-12 |  | Data Meeting | Disseminate Data Meeting Memo | Data Meeting Memo Template |  | Reading Teacher | K-5 Teachers | 4
School A | 03_October | 2020-10-13 | 3:15-4:15 | Staff Mtg | Workshop on the Reading Brain | Training Materials | School Cafeteria | External Facilitator | K-5 Teachers | 3
School A | 03_October | 2020-10-19 | Full Day | Data Meeting | Fall Benchmark Data Meetings | Data Management System, Reports | School Library | Reading Teacher | K-5 Teachers | 4
School B | 03_October | 2020-10-20 | Full Day | Data Meeting | Fall Benchmark Data Meetings | Data Management System, Reports | School Conference Room | Reading Teacher | K-5 Teachers | 4
District | 03_October | 2020-10-23 |  | Testing | Communicate Progress Monitoring Plan & distribute materials | Progress Monitoring Materials, PM Calendar |  | Reading Teacher | K-5 Teachers | 4
District | 03_October | 10/12/20 -10/14/20 |  | Testing | Import student data into data management system | Data Management System |  | District Tech |  | 4
District | 03_October | 10/12/20 -10/16/20 |  | Testing | Prepare for Data Meetings | Meeting Agenda Template, Reports |  | Reading Teacher |  | 4

## Assessment_with Continnuum (hidden)
Red - District Tech |  | Blue - HILL Tech |  | Green - HILL Facilitator |  | Purple - District Contact
District/School | Date | Time/ Hours | Activity/Topic | Materials Needed | Facilitator | Attendees | Goal
| Summer |  | Migrate Students in Assessment Systems & enable progress monitoring if all are being enabled | Assessment Systems | District Tech |  | 4 | Disseminate logins
| Prior to Workbook Toolkit Training if applicable |  | Create or update “Lists of People, Programs and Tests”, confirm any changes needed to dropdowns & send to HILL | “Lists of People, Programs and Tests” | District Contact |  | 4 | Facilitator Mock Meeting
| Prior to Workbook Toolkit Training if applicable |  | Update “Lists of People, Programs and Tests” and dropdowns in workbook | “Lists of People, Programs and Tests” | HILL Tech |  | 4
| Prior to Workbook Toolkit Training if applicable |  | Prepare student roster excel file. | Assessment or Student Management System | District Tech Contact |  | 4
| Summer | 1/2 day | Workbook Toolkit Training (Full day if the creation of workbook is embedded) | Workbook Toolkit, handouts, Toolkit User Guide | HILL Facilitator | District Tech Contact. &/or Internal Facilitator | 4
| Summer | 3+ | Generate Workbook from Scratch | Workbook Toolkit, “List of People Programs and Tests”, “Toolkit User Guide” | HILL/District Tech Contact |  | 4
| Summer | 1.5+ | Generate Workbook from prev. school year’s | Workbook from previous SY, “List of People Programs and Tests”, “Toolkit User Guide” | HILL/District Tech Contact |  | 4
| Aug/Sept | 3+ hrs | Train the Trainer: Determining Instructional Focus Training | Facilitator’s Guide, Presentation, Hos, LCD & screen | External Facilitator | Admin, Coach, Facilitator | 4
| Aug/Sept | 2-3 hrs | Determining Instructional Focus Training | Facilitator’s Guide, Presentation, HOs, LCD & screen | Admin, Coach, Facilitator | Teachers | 4
| Aug/Sept | 2 hrs | DIBELS Refresher Training | DIBELS Refresher Materials |  | Teachers | 4
| 3 days prior to data meeting |  | Year 2+ Schools: Deliver Workbook to data meeting facilitators | Data Grouping Workbook | External coach or HILL/District Tech Contact |  | 4
| 1-week window before Mtgs |  | Prepare for Data Meetings | “Initial Data Meeting Preparation Checklist” | External or Internal Mtg Facilitator |  | 4
| Sept | 30 min | Year 2+ Schools: Review Workbook & confirm that it is ready | Data Grouping Workbook | External or Internal Data Mtg Facilitator |  | 4
| Sept | 1 hr./ grade level | Year 2+ Schools: Sept. Initial Meetings | Data Grouping Workbooks | External or Internal Mtg Facilitator | Teachers, Interventionists, SPED, RT (No K Teachers) | 4
| Sept |  | Year 2+ Schools: Groups Begin | Workbook Printouts | Teachers, Interventionists, SPED, RT |  | 4
| Sept: At least 1 week before testing window |  | Disseminate Testing Memo | “Fall Testing Memo Template” | Internal coach or Admin. | Teachers | 4
| Sept: At least 1 week before testing window |  | Populate and disseminate Data Entry Form for non-electronic assessments | “Data Entry Form Example” | Internal coach, or HILL/District Tech Contact | Teachers | 4
| 2 weeks in Sept |  | Fall Testing Window | Testing Materials, Stopwatches | Teachers | Students | 4
| Sept (last day of testing or next school day) |  | Data Entry Due Date | Data Systems | Coaches, Teachers |  | 4
| Sept: Close of testing window |  | Confirm data entry is complete & export student data | Data Systems | District Tech. contact | Coaches, Teachers | 4
| Sept: Close of testing window |  | Collect data entry forms for non-electronic assessments | “Data Entry Form” | District Tech. contact | Coaches, Teachers | 4
| Sept/Oct: At least 1 week before data meeting |  | Disseminate Data Meeting Memo | “Fall Data Meeting Memo Template” | Internal coach or Admin. | Teachers | 4
| Sept/Oct: 3 days following close of testing window | 1.5 hrs./ school | Prep workbook for data meetings | Data Grouping Workbook, Workbook Toolkit, Toolkit User Guide | External coach or HILL/District Tech Contact |  | 4
| Sept/Oct: 3 days prior to data meeting |  | Deliver Workbook to data meeting facilitators | Data Grouping Workbook | External coach or HILL/District Tech Contact |  | 4
| Sept/Oct: 1-week window before Mtgs |  | Prepare for Fall Data Meetings | “Fall Data Meeting Preparation Checklist” | External or Internal Mtg Facilitator |  | 4
| 3 days prior to data meeting | 30 min | Review Workbook & confirm that it is ready | Data Grouping Workbook | External or Internal Data Mtg Facilitator |  | 4
| 3 days prior to data meeting |  | Print Reports (& distribute where necessary) | Data Systems | External or Internal Mtg Facilitator | Teachers | 4
| Oct. – No sooner than 1 week after the close of testing window |  | Fall Data Meetings | Data Grouping Workbooks, Data System reports | External or Internal Mtg Facilitator | Teachers, Interventionists, SPED, RT | 4
|  |  | New Groups Begin | Workbook Printouts | Teachers, Interventionists, SPED, RT |  | 4
| Oct.: Within 1 week of Data Mtg |  | Communicate Progress Monitoring Plan & distribute materials | Prog. Mon. Calendar | Admin or Internal Facilitator | Teachers | 4
| Oct.: Within 1 week of Data Mtg |  | If not already done, enable progress monitoring for applicable students | Data Systems | Admin or Internal Facilitator |  | 4
| Nov. |  | District Literacy Leadership Meeting: Review District Data | SLP, Activity Timeline, Data Reports | External Facilitator | Leadership Team | 4
| Nov. | 2+ hrs | Train the Trainer: Aimlines to Instructional Focus Training | Facilitator’s Guide, Presentation, HOs, LCD & screen | External Facilitator | Admin, Coach, Facilitator | 4
| Nov. | 1-2 hrs | Aimlines to Instructional Focus Training | Facilitator’s Guide, Presentation, HOs, LCD & screen | Admin, Coach, Facilitator | Teachers (grade level teams format preferred) | 4
| End of Nov/Dec: 2-day window 5 days prior to data meeting | 15 min./ school | Prep workbook for data meetings | Data Grouping Workbook, Workbook Toolkit, Toolkit User Guide | External coach or HILL/District Tech Contact |  | 4
| End of Nov/Dec: 3 days prior to data meeting |  | Deliver Workbook to data meeting facilitators | Data Grouping Workbook | External coach or HILL/District Tech Contact |  | 4
| End of Nov/Dec: 3 days prior to data meeting | 5 min | Review Workbook & confirm that it is ready | Data Grouping Workbook | External or Internal Data Mtg Facilitator |  | 4
| End of Nov/Dec: At least 1 week before data meeting |  | Disseminate “Data Meeting Memo” | “Fall PM Data Meeting Memo Template” | Internal coach or Admin. | Teachers | 4
| End of Nov/Dec |  | Fall PM Data Meetings | Data Meeting Docs, Workbook, PM data reports | External or Internal Mtg Facilitator | Grade Level Teams and SPED, RS, Principal | 4
| End of Nov/Dec |  | New Groups Begin | Workbook Printouts | Teachers, Interventionists, SPED, RT |  | 4
| End of Nov/Dec: Within 1 week of Data Mtg |  | Communicate Progress Monitoring Plan & distribute materials | Prog. Mon. Calendar | Admin or. Internal Facilitator | Teachers | 4
| End of Nov/Dec: Within 1 week of Data Mtg |  | If not already done, enable progress monitoring for applicable students | Data Systems | Admin or Internal Facilitator |  | 4
| Jan. | 1 hr | DIBELS Refresher Training for new measures | DIBELS Refresher Materials |  | K & 1 Teachers | 4
| Jan.: At least 1 week before testing window |  | Disseminate Testing Memo | “Winter Testing Memo Template” | Internal coach or Admin. | Teachers | 4
| Jan.: At least 1 week before testing window |  | Populate and disseminate Data Entry Form for non-electronic assessments | “Data Entry Form Example” | Internal coach, Admin., or HILL/District Tech Contact | Teachers | 4
| Jan. |  | Winter Testing Window | Testing Materials, Stopwatches | Teachers | Students | 4
| Jan. |  | Data Entry Due Date | Data Systems | Coaches, Teachers |  | 4
| Jan.: Close of testing window |  | Confirm data entry is complete & export student data | Data Systems | District Tech. contact | Coaches, Teachers | 4
| Jan.: Close of testing window |  | Collect data entry forms for non-electronic assessments | “Data Entry Form” | District Tech. contact | Coaches, Teachers | 4
| Jan./Feb.: At least 1 week before data meeting |  | Disseminate Data Meeting Memo | “Winter Data Meeting Memo Template” | Internal coach or Admin. | Teachers | 4
| Jan./Feb.: 3 days following close of testing window | 1.5 hrs./ school | Prep workbook for data meetings | Data Grouping Workbook, Workbook Toolkit, Toolkit User Guide | External coach or HILL/District Tech Contact |  | 4
| Jan./Feb.: 3 days prior to data meeting |  | Deliver Workbook to data meeting facilitators | Data Grouping Workbook | External coach or HILL/District Tech Contact |  | 4
| Jan./Feb. | 30 min | Review Workbook & confirm that it is ready | Data Grouping Workbook | External or Internal Data Mtg Facilitator |  | 4
| Jan./Feb.: 3 days prior to data meeting |  | Print Reports (& distribute where necessary) | Data Systems | Internal coach or Admin. | Teachers | 4
| Jan./Feb.: No sooner than 1 week after the close of testing window |  | Winter Data Meetings | Data Grouping Workbooks, Data System reports, LCD & Screen | External or Internal Mtg Facilitator | Teachers, Interventionists, SPED, RT | 4
| Jan./Feb.: Within 1 week of Data Mtg |  | Communicate Progress Monitoring Plan & distribute materials | Prog. Mon. Calendar | Admin or Internal Facilitator | Teachers | 4
| Jan./Feb.: Within 1 week of Data Mtg |  | If not already done, enable progress monitoring for applicable students | Data Systems | Admin or Internal Facilitator |  | 4
| February/March |  | District Literacy Leadership Meeting: Review District Data | SLP, Activity Timeline, Data Reports | External Facilitator | Leadership Team | 4
| March: 2-day window 5 days prior to data meeting | 15 min./ school | Prep workbook for Spring PM data meetings | Data Grouping Workbook, Workbook Toolkit, Toolkit User Guide | External coach or HILL/District Tech Contact |  | 4
| March: 3 days prior to data meeting |  | Deliver Workbook to data meeting facilitators | Data Grouping Workbook | External coach or HILL/District Tech Contact |  | 4
| March: 3 days prior to data meeting | 5 min | Review Workbook & confirm that it is ready | Data Grouping Workbook | External or Internal Data Mtg Facilitator |  | 4
| March: At least 1 week before data meeting |  | Disseminate “Data Meeting Memo” | “Spring PM Data Meeting Memo Template” | Internal coach or Admin. | Teachers | 4
| March |  | Spring PM Data Meetings | Data Meeting Docs, Workbook, PM data reports | External or Internal Mtg Facilitator | Grade Level Teams and SPED, RS, Principal | 4
| March |  | New Groups Begin | Workbook Printouts | Teachers, Interventionists, SPED, RT |  | 4
| March: Within 1 week of Data Mtg |  | Communicate Progress Monitoring Plan & distribute materials | Prog. Mon. Calendar | Admin or. Internal Facilitator | Teachers | 4
| March: Within 1 week of Data Mtg |  | If not already done, enable progress monitoring for applicable students | Data Systems | Admin or Internal Facilitator |  | 4
| May/June: At least 1 week before testing window |  | Disseminate Testing Memo | “Winter Testing Memo Template” | Internal coach or Admin. | Teachers | 4
| May/June: At least 1 week before testing window |  | Populate and disseminate Data Entry Form for non-electronic assessments | “Data Entry Form Example” | Internal coach, Admin., or HILL/District Tech Contact | Teachers | 4
| May/June |  | Spring Testing Window | Testing Materials, Stopwatches | Teachers | Students | 4
| May/June |  | Data Entry Due Date | Data Systems | Coaches, Teachers |  | 4
| May/June: Close of testing window |  | Confirm data entry is complete & export student data | Data Systems | District Tech. contact | Coaches, Teachers | 4
| May/June: Close of testing window |  | Collect data entry forms for non-electronic assessments | “Data Entry Form” | District Tech. contact | Coaches, Teachers | 4
| May/June: At least 1 week before data meeting |  | Disseminate Data Meeting Memo | “Winter Data Meeting Memo Template” | Internal coach or Admin. | Teachers | 4
| May/June: 3 days following close of testing window | 1.5 hrs./ school | Prep workbook for data meetings | Data Grouping Workbook, Workbook Toolkit, Toolkit User Guide | External coach or HILL/District Tech Contact |  | 4
| May/June: 3 days prior to data meeting |  | Deliver Workbook to data meeting facilitators | Data Grouping Workbook | External coach or HILL/District Tech Contact |  | 4
| May/June | 30 min | Review Workbook & confirm that it is ready | Data Grouping Workbook | External or Internal Data Mtg Facilitator |  | 4
| May/June: 3 days prior to data meeting |  | Print Reports (& distribute where necessary) | Data Systems | Internal coach or Admin. | Teachers | 4
| May/June: No sooner than 1 week after the close of testing window |  | Winter Data Meetings | Data Grouping Workbooks, Data System reports, LCD & Screen | External or Internal Mtg Facilitator | Teachers, Interventionists, SPED, RT | 4

## Other Activities (hidden)
District/ School | Date | Time/ Hours | Activity/Topic | Materials Needed | Facilitator | Attendees | Goal
| Nov, March, June |  | District Admin Check-Ins | DLP, Activity Timeline, PD Plan |  | HILL Facilitator, District Initiative Leaders | 1, 2, 3, 4
| Monthly |  | District Admin Meeting | DLP, Activity Timeline, PD Plan |  | External and Internal Admin Teams | 1, 2, 3, 4
| Monthly |  | Coaches Meeting | Calendars, Activity Timelines, DLP, Data Meeting Process | HILL Facilitator | Internal Coaches | 1, 2, 3, 4
| Monthly | .5 day | School-based Implementation Support |  | HILL Facilitator | Internal Coaches | 2, 3
| Aug/ Sept |  | First Day of School
| September |  | Initial School Meetings | Meeting Agenda, DLP, Activity Timeline, School Rosters | HILL Facilitator | Principals, Internal Coaches | 1, 2, 3, 4

## Previous Color Coding (hidden)
Date | Time/ Hours | Activity/Topic | Materials Needed | Facilitator | Attendees | Goal
Summer |  | Migrate Students in Assessment. Systems & enable progress monitoring if all are being enabled. | Assessment Systems | District Tech Contact |  | 4.2
Prior to Workbook Toolkit Training if applicable |  | Create or update “Lists of People, Programs and Tests”. | “Lists of People, Programs and Tests” |  |  | 4.3
Prior to Workbook Toolkit Training if applicable |  | Prepare student roster excel file. | Assessment or Student Management System | District Tech Contact |  | 4.3
Summer | 1/2 day | Workbook Toolkit Training (Full day if the creation of workbook is embedded) | Workbook Toolkit, handouts, Toolkit User Guide | HILL | District Tech Contact. &/or Internal Facilitator | 4.4
Summer | 3+ | Generate Workbook from Scratch | Workbook Toolkit, “List of People Programs and Tests”, “Toolkit User Guide” | HILL/District Tech Contact |  | 4.4
Summer | 1.5+ | Generate Workbook from prev. school year’s | Workbook from previous SY, “List of People Programs and Tests”, “Toolkit User Guide” | HILL/District Tech Contact |  | 4.4
Aug/Sept | 3+ hrs | Train the Trainer: Determining Instructional Focus Training | Facilitator’s Guide, Presentation, Hos, LCD & screen | External Facilitator | Admin, Coach, Facilitator | 4.1
Aug/Sept | 2-3 hrs | Determining Instructional Focus Training | Facilitator’s Guide, Presentation, HOs, LCD & screen | Admin, Coach, Facilitator | Teachers | 4.1
Aug/Sept | 2 hrs | DIBELS Refresher Training | DIBELS Refresher Materials |  | Teachers | 4.1
3 days prior to data meeting |  | Year 2+ Schools: Deliver Workbook to data meeting facilitators | Data Grouping Workbook | External coach or HILL/District Tech Contact |  | 4.3
1-week window before Mtgs |  | Prepare for Data Meetings | “Initial Data Meeting Preparation Checklist” | External or Internal Mtg Facilitator |  | 4.1
Sept | 30 min | Year 2+ Schools: Review Workbook & confirm that it is ready | Data Grouping Workbook | External or Internal Data Mtg Facilitator |  | 4.3
Sept | 1 hr./ grade level | Year 2+ Schools: Sept. Initial Meetings | Data Grouping Workbooks | External or Internal Mtg Facilitator | Teachers, Interventionists, SPED, RT (No K Teachers) | 4.1
Sept |  | Year 2+ Schools: Groups Begin | Workbook Printouts | Teachers, Interventionists, SPED, RT |  | 4.1
Sept: At least 1 week before testing window |  | Disseminate Testing Memo | “Fall Testing Memo Template” | Internal coach or Admin. | Teachers | 4.2
Sept: At least 1 week before testing window |  | Populate and disseminate Data Entry Form for non-electronic assessments | “Data Entry Form Example” | Internal coach, or HILL/District Tech Contact | Teachers | 4.2
2 weeks in Sept |  | Fall Testing Window | Testing Materials, Stopwatches | Teachers | Students | 4.2
Sept (last day of testing or next school day) |  | Data Entry Due Date | Data Systems | Coaches, Teachers |  | 4.2
Sept: Close of testing window |  | Confirm data entry is complete & export student data | Data Systems | District Tech. contact | Coaches, Teachers | 4.3
Sept: Close of testing window |  | Collect data entry forms for non-electronic assessments | “Data Entry Form” | District Tech. contact | Coaches, Teachers | 4.3
Sept/Oct: At least 1 week before data meeting |  | Disseminate Data Meeting Memo | “Fall Data Meeting Memo Template” | Internal coach or Admin. | Teachers | 4.1
Sept/Oct: 3 days following close of testing window | 1.5 hrs./ school | Prep workbook for data meetings | Data Grouping Workbook, Workbook Toolkit, Toolkit User Guide | External coach or HILL/District Tech Contact |  | 4.4
Sept/Oct: 3 days prior to data meeting |  | Deliver Workbook to data meeting facilitators | Data Grouping Workbook | External coach or HILL/District Tech Contact |  | 4.3
Sept/Oct: 1-week window before Mtgs |  | Prepare for Fall Data Meetings | “Fall Data Meeting Preparation Checklist” | External or Internal Mtg Facilitator |  | 4.1
3 days prior to data meeting | 30 min | Review Workbook & confirm that it is ready | Data Grouping Workbook | External or Internal Data Mtg Facilitator |  | 4.3
3 days prior to data meeting |  | Print Reports (& distribute where necessary) | Data Systems | External or Internal Mtg Facilitator | Teachers | 4.1
Oct. – No sooner than 1 week after the close of testing window |  | Fall Data Meetings | Data Grouping Workbooks, Data System reports | External or Internal Mtg Facilitator | Teachers, Interventionists, SPED, RT | 4.1
|  | New Groups Begin | Workbook Printouts | Teachers, Interventionists, SPED, RT |  | 4.1
Oct.: Within 1 week of Data Mtg |  | Communicate Progress Monitoring Plan & distribute materials | Prog. Mon. Calendar | Admin or Internal Facilitator | Teachers | 4.2
Oct.: Within 1 week of Data Mtg |  | If not already done, enable progress monitoring for applicable students | Data Systems | Admin or Internal Facilitator |  | 4.2
Nov. |  | District Literacy Leadership Meeting: Review District Data | SLP, Activity Timeline, Data Reports | External Facilitator | Leadership Team | 4.1
Nov. | 2+ hrs | Train the Trainer: Aimlines to Instructional Focus Training | Facilitator’s Guide, Presentation, HOs, LCD & screen | External Facilitator | Admin, Coach, Facilitator | 4.1
Nov. | 1-2 hrs | Aimlines to Instructional Focus Training | Facilitator’s Guide, Presentation, HOs, LCD & screen | Admin, Coach, Facilitator | Teachers (grade level teams format preferred) | 4.1
End of Nov/Dec: 2-day window 5 days prior to data meeting | 15 min./ school | Prep workbook for data meetings | Data Grouping Workbook, Workbook Toolkit, Toolkit User Guide | External coach or HILL/District Tech Contact |  | 4.4
End of Nov/Dec: 3 days prior to data meeting |  | Deliver Workbook to data meeting facilitators | Data Grouping Workbook | External coach or HILL/District Tech Contact |  | 4.3
End of Nov/Dec: 3 days prior to data meeting | 5 min | Review Workbook & confirm that it is ready | Data Grouping Workbook | External or Internal Data Mtg Facilitator |  | 4.3
End of Nov/Dec: At least 1 week before data meeting |  | Disseminate “Data Meeting Memo” | “Fall PM Data Meeting Memo Template” | Internal coach or Admin. | Teachers | 4.1
End of Nov/Dec |  | Fall PM Data Meetings | Data Meeting Docs, Workbook, PM data reports | External or Internal Mtg Facilitator | Grade Level Teams and SPED, RS, Principal | 4.1
End of Nov/Dec |  | New Groups Begin | Workbook Printouts | Teachers, Interventionists, SPED, RT |  | 4.1
End of Nov/Dec: Within 1 week of Data Mtg |  | Communicate Progress Monitoring Plan & distribute materials | Prog. Mon. Calendar | Admin or. Internal Facilitator | Teachers | 4.2
End of Nov/Dec: Within 1 week of Data Mtg |  | If not already done, enable progress monitoring for applicable students | Data Systems | Admin or Internal Facilitator |  | 4.2
Jan. | 1 hr | DIBELS Refresher Training for new measures | DIBELS Refresher Materials |  | K & 1 Teachers | 4.1
Jan.: At least 1 week before testing window |  | Disseminate Testing Memo | “Winter Testing Memo Template” | Internal coach or Admin. | Teachers | 4.2
Jan.: At least 1 week before testing window |  | Populate and disseminate Data Entry Form for non-electronic assessments | “Data Entry Form Example” | Internal coach, Admin., or HILL/District Tech Contact | Teachers | 4.2
Jan. |  | Winter Testing Window | Testing Materials, Stopwatches | Teachers | Students | 4.2
Jan. |  | Data Entry Due Date | Data Systems | Coaches, Teachers |  | 4.2
Jan.: Close of testing window |  | Confirm data entry is complete & export student data | Data Systems | District Tech. contact | Coaches, Teachers | 4.3
Jan.: Close of testing window |  | Collect data entry forms for non-electronic assessments | “Data Entry Form” | District Tech. contact | Coaches, Teachers | 4.3
Jan./Feb.: At least 1 week before data meeting |  | Disseminate Data Meeting Memo | “Winter Data Meeting Memo Template” | Internal coach or Admin. | Teachers | 4.1
Jan./Feb.: 3 days following close of testing window | 1.5 hrs./ school | Prep workbook for data meetings | Data Grouping Workbook, Workbook Toolkit, Toolkit User Guide | External coach or HILL/District Tech Contact |  | 4.4
Jan./Feb.: 3 days prior to data meeting |  | Deliver Workbook to data meeting facilitators | Data Grouping Workbook | External coach or HILL/District Tech Contact |  | 4.3
Jan./Feb. | 30 min | Review Workbook & confirm that it is ready | Data Grouping Workbook | External or Internal Data Mtg Facilitator |  | 4.3
Jan./Feb.: 3 days prior to data meeting |  | Print Reports (& distribute where necessary) | Data Systems | Internal coach or Admin. | Teachers | 4.1
Jan./Feb.: No sooner than 1 week after the close of testing window |  | Winter Data Meetings | Data Grouping Workbooks, Data System reports, LCD & Screen | External or Internal Mtg Facilitator | Teachers, Interventionists, SPED, RT | 4.1
Jan./Feb.: Within 1 week of Data Mtg |  | Communicate Progress Monitoring Plan & distribute materials | Prog. Mon. Calendar | Admin or Internal Facilitator | Teachers | 4.2
Jan./Feb.: Within 1 week of Data Mtg |  | If not already done, enable progress monitoring for applicable students | Data Systems | Admin or Internal Facilitator |  | 4.2
February/March |  | District Literacy Leadership Meeting: Review District Data | SLP, Activity Timeline, Data Reports | External Facilitator | Leadership Team | 4.1
March: 2-day window 5 days prior to data meeting | 15 min./ school | Prep workbook for Spring PM data meetings | Data Grouping Workbook, Workbook Toolkit, Toolkit User Guide | External coach or HILL/District Tech Contact |  | 4.4
March: 3 days prior to data meeting |  | Deliver Workbook to data meeting facilitators | Data Grouping Workbook | External coach or HILL/District Tech Contact |  | 4.3
March: 3 days prior to data meeting | 5 min | Review Workbook & confirm that it is ready | Data Grouping Workbook | External or Internal Data Mtg Facilitator |  | 4.3
March: At least 1 week before data meeting |  | Disseminate “Data Meeting Memo” | “Spring PM Data Meeting Memo Template” | Internal coach or Admin. | Teachers | 4.1
March |  | Spring PM Data Meetings | Data Meeting Docs, Workbook, PM data reports | External or Internal Mtg Facilitator | Grade Level Teams and SPED, RS, Principal | 4.1
March |  | New Groups Begin | Workbook Printouts | Teachers, Interventionists, SPED, RT |  | 4.1
March: Within 1 week of Data Mtg |  | Communicate Progress Monitoring Plan & distribute materials | Prog. Mon. Calendar | Admin or. Internal Facilitator | Teachers | 4.2
March: Within 1 week of Data Mtg |  | If not already done, enable progress monitoring for applicable students | Data Systems | Admin or Internal Facilitator |  | 4.2
May/June: At least 1 week before testing window |  | Disseminate Testing Memo | “Winter Testing Memo Template” | Internal coach or Admin. | Teachers | 4.2
May/June: At least 1 week before testing window |  | Populate and disseminate Data Entry Form for non-electronic assessments | “Data Entry Form Example” | Internal coach, Admin., or HILL/District Tech Contact | Teachers | 4.2
May/June |  | Spring Testing Window | Testing Materials, Stopwatches | Teachers | Students | 4.2
May/June |  | Data Entry Due Date | Data Systems | Coaches, Teachers |  | 4.2
May/June: Close of testing window |  | Confirm data entry is complete & export student data | Data Systems | District Tech. contact | Coaches, Teachers | 4.3
May/June: Close of testing window |  | Collect data entry forms for non-electronic assessments | “Data Entry Form” | District Tech. contact | Coaches, Teachers | 4.3
May/June: At least 1 week before data meeting |  | Disseminate Data Meeting Memo | “Winter Data Meeting Memo Template” | Internal coach or Admin. | Teachers | 4.1
May/June: 3 days following close of testing window | 1.5 hrs./ school | Prep workbook for data meetings | Data Grouping Workbook, Workbook Toolkit, Toolkit User Guide | External coach or HILL/District Tech Contact |  | 4.4
May/June: 3 days prior to data meeting |  | Deliver Workbook to data meeting facilitators | Data Grouping Workbook | External coach or HILL/District Tech Contact |  | 4.3
May/June | 30 min | Review Workbook & confirm that it is ready | Data Grouping Workbook | External or Internal Data Mtg Facilitator |  | 4.3
May/June: 3 days prior to data meeting |  | Print Reports (& distribute where necessary) | Data Systems | Internal coach or Admin. | Teachers | 4.1
May/June: No sooner than 1 week after the close of testing window |  | Winter Data Meetings | Data Grouping Workbooks, Data System reports, LCD & Screen | External or Internal Mtg Facilitator | Teachers, Interventionists, SPED, RT | 4.1