# MASSACHUSETTS DEPARTMENT OF ELEMENTARY AND SECONDARY EDUCATION

# Public School Monitoring

# Integrated Monitoring Review

# Corrective Action Plan

# District: Duxbury Public School District

# Monitoring Onsite Year: 2025-2026

# Program Area: Special Education

All corrective action must be fully implemented and all noncompliance corrected as soon as possible and no later than one year from the issuance of the Integrated Monitoring Review Final Report dated 04/24/2026.

Mandatory One-Year Compliance Date: 04/24/2027

## Summary of Required Corrective Action

| Criterion | Criterion Title | Rating |
| --- | --- | --- |
| SE 9 | Timeline for determination of eligibility | Partially Implemented |
| SE 18B | Determination of placement; provision of IEP to parent | Partially Implemented |
| SE 37 | Procedures for approved and unapproved out-of-district placements | Partially Implemented |

Integrated Monitoring Review
Special Education and Civil Rights Corrective Action Plan

## Local Education Agency Response

Criterion & Topic: SE 9 Timeline for determination of eligibility

IMR Rating: Partially Implemented

Department Findings:

A review of student records and staff interviews indicated that within 45 school working days after receipt of the parent's written consent to an initial evaluation or reevaluation, the district does not always determine whether the student is eligible for special education and provide the parent with the proposed IEP and proposed placement.

Description of Root Cause Analysis:

The district conducted a root cause analysis which indicated that the non-compliance was the result of an additional signed consent received from the parent for testing in an area not included in the original consent. The district disregarded the earlier consent date and started the count for the timeline based on the second consent date leading to the noncompliance.

Title/Role(s) of Responsible Persons:

Director of Special Education, Bernard McNamara

Expected Date of Completion:

12/18/2026

Evidence of Completion of the Corrective Action:

Updated procedures, a timeline tracker, agenda for staff training, verification of attendance and results of the Department's record review.

Description of Internal Monitoring Procedures:

The Special Education Director will conduct quarterly internal record review to ensure that within 45 school working days after receipt of the parent's written consent to an initial evaluation or reevaluation, the district determines whether the student is eligible for special education and provides the parent with the proposed IEP and proposed placement, where applicable. The district will conduct annual training for all relevant staff on initial and reevaluation timeline requirements.

## Department Approval Section

Criterion: SE 9 Timeline for determination of eligibility

Corrective Action Plan Status: Approved

Status Date: 05/19/2026

Correction Status: Not Corrected

Required Elements of Progress Report(s):

By June 30, 2026, the district will submit updated procedures, a tracker for tracking the IEP timeline to ensure the issuance of IEPs to parents within 45 school days of receiving a written consent to evaluate.

By September 25, 2026, the district will submit evidence of staff training on the updated procedures including agenda for staff training and verification of attendance.

By November 14, 2026, the Department will conduct a review of additional student records to ensure initial evaluation timelines for eligibility determination requirements are met. For any identified non-compliance, the district will conduct a root cause analysis and implement appropriate corrective actions. Additional progress reports may be required.

Progress Report Due Date(s):

06/30/2026

## Local Education Agency Response

Criterion & Topic: SE 18B Determination of placement; provision of IEP to parent

IMR Rating: Partially Implemented

Department Findings:

A review of student records and staff interviews indicated that the district does not always issue the proposed IEP and proposed placement to the parent immediately following the development of the IEP.

Description of Root Cause Analysis:

The district conducted a root cause analysis which indicated that a Team Chair interpreted the new 5-day requirement to provide the IEP to parents as only being applicable during an initial evaluation or 3-year re-revaluation (e.g., when the flowchart was completed).

Title/Role(s) of Responsible Persons:

Director of Special Education, Bernard McNamara

Expected Date of Completion:

12/18/2026

Evidence of Completion of the Corrective Action:

Evidence of reconvening the Team for the student identified by the Department to consider the need for compensatory services, including meeting invitation, meeting attendance, N1 and a plan for compensatory services, if applicable.

Updated procedures, tracker, agenda for staff training, verification of attendance and results of the Department's record review.

Description of Internal Monitoring Procedures:

The Special Education Director will conduct quarterly internal record review to ensure that the district issues the proposed IEP and proposed placement to the parent immediately following the development of the IEP. The district will conduct annual training for all relevant staff on the issuance of IEPs within 5 days following any Team meetings.

## Department Approval Section

Criterion: SE 18B Determination of placement; provision of IEP to parent

Corrective Action Plan Status: Approved

Status Date: 05/19/2026

Correction Status: Not Corrected

Required Elements of Progress Report(s):

By June 30,2026, the district will submit evidence of reconvening the Team for the student identified by the Department to consider the need for compensatory services, including meeting invitation, meeting attendance, N1 and a plan for compensatory services, if applicable.

By June 30, 2026, the district will submit updated procedures and a tracker for tracking the issuance of IEPs to parents within 5 days following any Team meeting.

By September 25, 2026, the district will submit evidence of staff training on the updated procedures and the tracker, including training agenda and verification of attendance.

By November 14, 2026, the Department will conduct a review of additional student records to ensure the immediate issuance of IEPs to parents and guardians following a Team meeting. For any identified non-compliance, the district will conduct a root cause analysis and implement appropriate corrective actions. Additional progress reports may be required.

Progress Report Due Date(s):

06/30/2026

## Local Education Agency Response

Criterion & Topic: SE 37 Procedures for approved and unapproved out-of-district placements

IMR Rating: Partially Implemented

Department Findings:

A review of student records and interviews indicated that the district's written contracts with out-of-district placements do not include a nondiscrimination statement.

Description of Root Cause Analysis:

The district conducted a root cause analysis which indicated that the lack of a template for out-of-district placement agreement that contains all the required information in the Special Education Procedures Manual contributed to the noncompliance.

Title/Role(s) of Responsible Persons:

Director of Special Education

Expected Date of Completion:

12/18/2026

Evidence of Completion of the Corrective Action:

Updated out-of-district placement contract template that includes an accurate nondiscrimination policy statement, checklist for all the required components of out-of-district placement contract, agenda for staff training, verification of attendance, results of the Department's record review.

Description of Internal Monitoring Procedures:

The Special Education Director will conduct quarterly internal record review to ensure that the written contracts for out-of-district placements meet all the requirements. The district will conduct annual training for all relevant staff on the requirements for out-of- district placement contracts.

## Department Approval Section

Criterion: SE 37 Procedures for approved and unapproved out-of-district placements

Corrective Action Plan Status: Approved

Status Date: 05/19/2026

Correction Status: Not Corrected

Required Elements of Progress Report(s): By June 30, 2026, the district will submit updated out-of-district contract template, and a checklist for ensuring out of district placement contracts include all the required information. By September 25, 2026, the district will submit evidence of staff training on the requirements for out of district placement contracts and the checklist. Evidence will include training agenda and verification of attendance.

By November 14, 2026, the Department will conduct a review of additional student records to ensure all out-of-district placement contracts meet requirements. For any identified non-compliance, the district will conduct a root cause analysis and implement appropriate corrective actions. Additional progress reports may be required.

Progress Report Due Date(s):

06/30/2026